## Cover
User Acceptance Testing
Project name | Thesis Similarity Search
Features in scope | Search
Build version | 1.0.0
UAT environment | localhost
UAT schedule | 2025-12-11
Tester | Mario

## Acceptance Criteria
ID | Acceptance Criteria Description
AC-1 | Users must able to appear Thesis List with all details exactly as entered.
AC-2 | The search function must be case-insensitive (e.g., searching for a category "analisis" also finds "Analisis").
AC-3 | Users must able to search authors name directly and appear in the Thesis List

## Test Cases
Test ID | AC | Test Scenario | Test Steps | Expected Result | Actual Result | Pass / Fail
UAT-001 | AC-1 | Default settings of thesis search | 1. Open app. 2. Fill in search field: Analisis 3. Press enter. 4. Click arrow on the right side. | Show a list of authors of similar thesis name with "Analisis" | "Analisis" appears in the list of authors of similar thesis name | Pass
UAT-002 | AC-1 | Search similar thesis filtered by author's program | 1. Click settings icon. 2. Select 'Informatics' in filter by programs field 3. Click x icon for close settings modal. 4. Fill in search field: Analisis 5. Press enter. 6. Click arrow on the right side. | Show a list of authors that only informatics lecturer who had similar thesis name with "Analisis" | Show a list of authors that only informatics lecturer who had similar thesis name with "Analisis" | Pass
UAT-003 | AC-1 | Searching for similar thesis name/papers | 1. Click settings icon. 2. Change search type 'Author' into 'Paper'. 3. Click x icon for close settings modal. 4. Fill in search field: Analisis 5. Press enter. | Show a list of papers of similar thesis name with "Analisis" | Show a list of papers of similar thesis name with "Analisis" | Pass
UAT-004 | AC-1 | Searching for similar thesis name using other model | 1. Click settings icon. 2. Select search type 'Paper'. 3. Change model into 'all-MiniLM-L6-v2' or 'IndoBERT (Fine-tuned)' 3. Click x icon for close settings modal. 4. Fill in search field: Analisis 5. Press enter. | Show a list of papers of similar thesis name with "Analisis" | Show a list of papers of similar thesis name with "Analisis" | Pass
UAT-005 | AC-1 | Searching for top 5 similar thesis name | 1. Click settings icon. 2. Select search type 'Paper'. 3. Select any model 4. Change Top K input into '5' 3. Click x icon for close settings modal. 4. Fill in search field: Analisis 5. Press enter. | Show a list with only top 5 papers of similar thesis name with "Analisis" | Show a list with only top 5 papers of similar thesis name with "Analisis" | Pass
UAT-006 | AC-2 | Case-insensitive input | 1. Click settings icon. 2. Select search type 'Paper'. 3. Click x icon for close settings modal. 4. Fill in search field: Analisa 5. Press enter. 6. Compare with Fill in search field: analisa 7. Press enter | App will showing the same list because both are the same word | App shows different list of thesis names (mostly it has 'Analisa' in front of thesis name because the 'A' is capital letter, and 'analisa' in the middle of thesis name) | Fail
UAT-007 | AC-3 | Searching authors name by input author name directly | 1. Click settings icon. 2. Select search type 'Author'. 3. Click x icon for close settings modal. 4. Fill in search field: Alexander Setiawan 5. Press enter. | App will show the result as search input as author's name at the top of the list | It doesn't show the author's name at the top of list, not even in the list with 100 Top K | Fail

## Defect Log
ID | Test ID | Defect Description | Expected Result | Actual Result | Severity
DL-1 | UAT-001 | Pagination feature automaticaly changing to show 4 items per page when selecting number of page or clicking next and previous page even though its was already set 50, 20, or other numbers of items per page | If app successfully searching 100 thesis names, when user set 50 items per page, it should show another 50 thesis names in page number 2 | The app repeat to show the first four thesis names and automaticaly set 4 items per page | Low